## Automation Status - 19th Aug
Track | #Priority | # Scenarios | Pending Scenarios | Completed | Completion % | ETA | Challenges | Remarks | Prod Scenarios | Open Defects(Total Defect)
KPIs (Account Overview, S&S, Device, License, All Device Flyout) | P1 | 14 | 0 | 14 | 100% | Completed | Automated with MCE 2.0. This will not work with MCE 1.0 | Jobs scheduled in Orchestrator for both Stage and PROD | 14 | 2 (3)
eDelivery | P1 | 14 | 2 | 12 | 85.71% | Almost done | Once MCE 1.0 is enabled we will check and get back to you on rework effort. | Job scheduled in Orchestrator for Stage environemnt. 2 TC pending 1.TC - pending due to test data unavailability (Partially Assigned) 2.Send OBA email verification in Outlook – Not feasible to automation due to 2-Factor Authentication | 2
Version Upgrade | P1 | 25 | 10 | 15 | 60% | WIP | Once MCE 1.0 is enabled we will check and get back to you on rework effort.
Global Search | P2 | 12 | 10 | 2 | 16.67% | WIP | Need to check once MCE 1.0 is enabled w.r.t Impact
IDV – Devices, S&S, Dashboard | P2 | 37 | 34 | 3 | 8.108% |  | Few scenarios related to MCE 2.0. 17 (out of 37)- We can proceed with MCE 1.0 | Analysis Completed
Total |  | 102 | 56 | 46 | 45.1%
CLEO | P3 | 37 | 6 | 31 | 83.78% |  | Automated with MCE 2.0. | On HOLD due to first five track prioritized | 6
Non CLEO | P3 | 27 | 7 | 20 | 74.07% |  | Automated with MCE 2.0. | On HOLD due to first five track prioritized
Total |  | 64 | 13 | 51 | 79.69%
Overall Total |  | 166 | 69 | 97 | 58.43% |  |  |  | 22

## eDelivery
# | Test Case description | Automated | Test Script Name | Remarks
1 | No SA flow for Customer and Partner Users | Y | Folder : MCEPROD1\eDelivery eDelivery_TC01_NoSAFlowForCustomer.xaml | Customer - mbrossas - marie-agnes.brossas@bull.net / Cisco123- no SA Partner - Required test data? michaelsscott - mike.scott@global.ntt / cisco123- access level 3 - This is having SA kevwailes -kevin@rj-ipt.com - access level 2 - This is having SA
2 | eDelivery_SA selection is retained for customer with multiple SA | Y | Folder : MCEPROD1\eDelivery Name : eDelivery_TC02_SASelectionwithMultipleSAs_Customer.xaml | nelson.jared@dorsey.com / cisco123
3 | eDelivery_Verify DDC Registration page, if user enters wrong combination of SO#,serial Number & DDC, then system will throw error | Y | Folder : MCEPROD1\eDelivery Name : eDelivery_TC06_DDC Reg. page with wrong combination | https://mce-stage.cisco.com/mce/#/edelivery/ddc
4 | Verification of software central eDelivery url is redirecting to MCE eDelivery | Y | Folder : MCEPROD1\eDelivery Name : eDelivery_TC04_Software central eDelivery_redirecting to MCE eDelivery.xaml | https://software-stage1.cisco.com/
5 | Verify if SA/VA names selections are greyed out in User view | Y | Folder : MCEPROD1\eDelivery Name : eDelivery_TC05_SAVACheckinUserView.xaml
6 | SA column in Order Summary User view page is populated | Y | Folder : MCEPROD1\eDelivery Name : eDelivery_TC06_SA_Column_OrderSummary.xaml
7 | Verify if Account view is not visible in orders tab for doman mismatch external users | Y | Folder : MCEPROD1\eDelivery Name : eDelivery_TC07_Account view is not visible in orders tab.xaml | kevin@rj-ipt.com / cisco123
8 | eDelivery_Verify DDC registration page, on correct combination of SO# and DDC, take user to order detail page | Y | Folder : MCEPROD1\eDelivery Name : eDelivery_TC08_DDC Reg. page with correct Order and DDC.xaml | https://mce-stage.cisco.com/mce/#/edelivery/ddc Test data : Order#112140079 DDC: W1L6ER-2CXN7K-PAA94X-9CQ2UC
9 | TC_Validate Search | Y | Folder : MCEPROD1\eDelivery Name : eDelivery_TC09_ValidateSearch
10 | Verification of event history, download history, Send OBA pages through inline actions in Order detail page for single line | Y | Folder : MCEPROD1\eDelivery Name : eDelivery_TC09_ValidateSearch
11 | Verify if Send OBA events are captured in event history and Send OBA history | Y | Folder : MCEPROD1\eDelivery Name : eDelivery_TC10_SendOBA_EventHistoryCheck.xaml | 108940015
12 | Verify if Software, EULA, License download are successful | Y | Folder : MCEPROD1\eDelivery Name : eDelivery_TC11_Software_EULA_License_download_success.xaml
13 | Verify is user is receving success message and receives email on Send OBA |  |  | Subscribe - https://mailer.cloudapps.cisco.com/itsm/mailer/subscribe.do?id=62540625
14 | Verify if SA column in Order Summary User view/Account viewpage is populated as "Partially Assigned" for order which has few lines assigned and few unassigned |  |  | Required Test Data
15 | TC2_Verify if user is landed to detail page on accessing OBA link | NA |  | Not valid for now
16 | TC24_eDelivery_Account view is not visible in order table | NA |  | Not valid for now

## Version Upgrade
S No | Scenarios | Description
1 | Create Order Page | Ensure the appropriate filters are displayed along with the Upgrade data on the Create Order Page
2 | Review Order Page | Ensure the appropriate ordered data entered on Create Order page is getting displayed and Place Order button is present for user to submit the Order once the email address is entered
3 | Accurate Order Quantity based on Max Order Quantity | Validate that the order quantity is calculated accordingly if the upgrade sku is setup with max orderable quantity and displayed to the user
4 | Appropriate Upgrade SKU's are displayed when differernt Filters are applied | Validate that the appropirate Upgrade SKU's are displayed when various filters are applied
5 | Docusign Load | Validate that the Docusign page is loading once the user places order on the review order page
6 | CCW Order Submission | Validate that the Order gets submitted and the Order# is displayed to the user on the Order Confirmation page once they complete signing the agreement
7 | Order Confirmation Email & History | Validate that the Order confirmation email is sent to the user with WebOrderID and the same is logged in History
8 | Customer User with Single SA/Single GU which roll up to logged In SA | 1.Validate the Customer user is redirected from Software Central portal to MCE portal -VU page and able to Submit Order when user having access to 1 SA and 1 Install- At GU that rolls up to that SA and can see the SA mode Account and User view toggle should not exists 2.Validate the Customer user is directly accessing MCE portal -VU page and able to Submit Order when user having access to 1 SA and 1 Install- At GU that rolls up to that SA and can see the SA mode Account and User view toggle should not exists
9 | Customer User with Single SA/Single GU which doesn't roll up to Logged in SA | 1.Validate the Customer user is redirected from Software Central portal to MCE portal -VU page and able to Submit Order in both Account and User view when user having access to 1 SA and 1 Install- At GU that rolls up to that SA and can see the SA mode Account and User view toggle should exists. verify VA column in Account View and Order SA/VA Column in User View if data exists in VU data grid 2.Validate the Customer user is directly accessing MCE portal -VU page and able to Submit Order in both Account and User view when user having access to 1 SA and 1 Install- At GU that rolls up to that SA and can see the SA mode Account and User view toggle should exists verify VA column in Account View and Order SA/VA Column in User View if data exists in VU data grid
10 | Customer User with single SA/Multiple GU's rolling up | 1.Verify the Customer user is redirected from Software Central portal to MCE portal -VU page and able to Submit Order in both Account and User viewwhen user having access to single SA and multiple Install-At GU's can see the SA mode Account View and User View toggle should Exist Once User Switches to User View, EC Gu pop-up should come up verify VA column in Account View and Order SA/VA Column in User View if data exists in VU data grid 2. Verify the Customer user is directly accessing MCE portal -VU page and able to Submit Order in both Account and User view when user having access to Single SA and multiple Install-At GU's can see the SA mode Account View and User View toggle should Exist Once User Switches to User View, EC Gu pop-up should come up verify VA column in Account View and Order SA/VA Column in User View if data exists in VU data grid
11 | Customer User with Multiple SA/single GU's redirected from PUT tool to MCE VU page or directly Accessing MCE portal | 1.Verify the Customer user is redirected from Software Central portal to MCE portal -VU page and able to Submit Order in both Account and User view when user having access to multiple SA and single Install-At GU's can see the SA mode Account View and User View toggle should Exist when User GU is not rolling up to SA Anchor GU Once User Switches to User View, EC Gu pop-up should not exists as user is having single GU verify VA column in Account View and Order SA/VA Column in User View if data exists in VU data grid 2. Verify the Customer user is directly accessing MCE portal -VU page and able to Submit Order in both Account and User view when user having access to Single SA and multiple Install-At GU's can see the SA mode Account View and User View toggle should Exist when User GU is not rolling up to SA Anchor GU Once User Switches to User View, EC Gu pop-up should not exists as user is having single GU verify VA column in Account View and Order SA/VA Column in User View if data exists in VU data grid
12 | Customer User with Multiple SA's/Multiple GU's | 1. Verify the Customer user is redirected from Software Central portal to MCE portal -VU page and able to Submit Order in both Account and User view when user having access to multiple SA's and multiple Install-At GU's can see the SA mode Account View and User View toggle should Exist Once User Switches to User View, EC Gu pop-up should exists as user is having access to multiple GU verify VA column in Account View and Order SA/VA Column in User View if data exists in VU data grid 2.Verify the Customer user is directly accessing MCE portal -VU page and able to Submit Order in both Account and User view when user having access to multiple SA's and multiple Install-At GU's can see the SA mode Account View and User View toggle should Exist Once User Switches to User View, EC Gu pop-up should exists as user is having access to multiple GU verify VA column in Account View and Order SA/VA Column in User View if data exists in VU data grid
13 | Customer User with no SA/single GU - "Proceed to Order Version Upgrade without a smart account" | 1.Verify the Customer user is redirected from Software Central portal to MCE portal -VU page and able to Submit Order when user not having access to any SA's but having single Install-At GU cannot see the SA mode Account and User View should not Exists as user is not having any SA Order SA/VA Column should exists in VU data grid 2.Verify the Customer user is directly accessing MCE portal -VU page and able to Submit Order when user not having access to any SA's but having single Install-At GU cannot see the SA mode Account and User View should not Exists as user is not having any SA Order SA/VA Column should exists in VU data grid
14 | Parnter User with no SA/multiple GU-"Proceed to Order Version Upgrade without a smart account" | 1.Verify the Customer user is redirected from Software Central portal to MCE portal -VU page and able to Submit Order by selecting one of EC GU when user not having access to any SA's but having multiple Install-At GU's can see secondary EC selector pop up Account and User View toggle should not Exists as user is not having any SA Order SA/VA Column should exists in VU data grid 2.Verify the Customer user is directly accessing MCE portal -VU page and able to Submit Order by selecting one of EC GU when user having access to multiple SA's and multiple Install-At GU's can see secondary EC selector popup Account and User View toggle should not Exists as user is not having any SA Order SA/VA Column should exists in VU data grid
15 | Any Partner user having atleast 1 SA will have both Options [SA option and Without SA option] - redirected from PUT tool to VU page or directly Accessing MCE portal | When User either redirects from Put tool or directly accessing MCE portal,Selector should be presented with both the options always to either go with Smart Account or without a Smart Account. SA Preference should not be persisted.
16 | Partner User with Single SA/Single GU | 1. Via PUT Tool After selecting SA option, User should be landed directly to Version Upgrade page with SA VA selector displayed on top right side After selecting No-SA option "Proceed to Portal without Smart Account", User should be landed directly to Version Upgrade page without SA VA selector in No SA Mode Account View and User View Toggle should not Exist Partner User should be able to submit order in both SA and No-SA modes 2. Directly Accessing MCE portal User should be landed directly to Account Overview page by choosing both options in SA Flow and No-SA Flow Marketing page information should be shown in Account Overview in No-SA mode Partner User should be able to submit order in both SA and No-SA modes
17 | Partner User with Single SA/Single GU which doesn't roll up to SA redirected from PUT tool to MCE VU page or directly accessing MCE portal by Choosing both Option | 1. Via PUT Tool After selecting SA option, User should be landed directly to Version Upgrade-AccountView page with SA VA selector displayed on top right side. Account View and User View Toggle should Exist in SA mode After selecting no-SA option "Proceed to Portal without Smart Account", User should be landed directly to Version Upgrade page without SA VA selector in No SA Mode Partner User should be able to submit order in both SA mode -( Account View and User View) and No-SA modes 2. Directly Accessing MCE portal User should be landed directly to Account Overview page by choosing both options in SA Flow and No-SA Flow Marketing page information should be shown in Account Overview in No-SA mode Account View and User View toggle should exists as user gu doesn't roll up to SA's GU Partner User should be able to submit order in both SA mode -( Account View and User View) and No-SA modes
18 | Partner User with single SA/Multiple GU's | 1. Via PUT Tool After selecting SA option, User should be landed directly to Version Upgrade-AccountView page with SA VA selector displayed on top right side. Account View and User View Toggle should Exist in SA mode. EC GU Selector should be shown up in User mode as user is having multiple GU's After selecting no-SA option "Proceed to Portal without Smart Account", User should be landed directly to Version Upgrade page without SA VA selector in No SA Mode Partner User should be able to submit order in both SA mode -( Account View and User View) and No-SA modes 2. Directly Accessing MCE portal User should be landed directly to Account Overview page by choosing both options in SA Flow and No-SA Flow Marketing page information should be shown in Account Overview in No-SA mode SA mode : Account View and User View toggle should exists only in SA mode NO-SA mode : EC GU Selector should be shown up as user is having multiple GU's Partner User should be able to submit order in both SA mode -( Account View and User View) and No-SA modes
19 | Partner User with Multiple SA/single GU's redirected from PUT tool to MCE VU page or directly Accessing MCE portal by Choosing both Option | 1. Via PUT Tool After selecting SA option, User should be landed directly to Version Upgrade-AccountView page with SA VA selector displayed on top right side.Account View and User View toggle should Exist when User GU is not rolling up to SA Anchor GU Once User Switches to User View, EC Gu pop-up should not exists as user is having single GU. if user selects SA which SA's GU is matching anchor gu, then Account View and User View toggle won't exist for that selected SA After selecting no-SA option "Proceed to Portal without Smart Account", User should be landed directly to Version Upgrade page without SA VA selector in No SA Mode Partner User should be able to submit order in both SA mode -( Account View and User View) and No-SA modes 2. Directly Accessing MCE portal User should be landed directly to Account Overview page by choosing both options in SA Flow and No-SA Flow Marketing page information should be shown in Account Overview in No-SA mode SA mode : Account View and User View toggle should Exist when User GU is not rolling up to SA Anchor GU Once User Switches to User View, EC Gu pop-up should not exists as user is having single GU. NO-SA mode : EC GU Selector should not be shown up as user is having single GU's Partner User should be able to submit order in both SA mode -( Account View and User View) and No-SA modes
20 | Partner User with Multiple SA's/Multiple GU's | 1. Via PUT Tool After selecting SA option, User should be landed directly to Version Upgrade-AccountView page with SA VA selector displayed on top right side. Account View and User View Toggle should Exist in SA mode. EC GU Selector should be shown up in User mode as user is having multiple GU's After selecting no-SA option "Proceed to Portal without Smart Account", User should be landed directly to Version Upgrade page without SA VA selector in No SA Mode Partner User should be able to submit order in both SA mode -( Account View and User View) and No-SA modes verify VA column in Account View and Order SA/VA Column in User View if data exists in VU data grid 2. Directly Accessing MCE portal User should be landed directly to Account Overview page by choosing both options in SA Flow and No-SA Flow Marketing page information should be shown in Account Overview in No-SA mode SA mode : Account View and User View toggle should exists only in SA mode NO-SA mode : EC GU Selector should be shown up as user is having multiple GU's Partner User should be able to submit order in both SA mode -( Account View and User View) and No-SA modes verify VA column in Account View and Order SA/VA Column in User View if data exists in VU data grid
21 | Partner User with no SA/single GU redirected from PUT tool to MCE VU page or directly accessing MCE portal using option "Proceed to Order Version Upgrade without a smart account" | 1.Verify the Partner user is redirected from Software Central portal to MCE portal -VU page and able to Submit Order when user not having access to any SA's but having single Install-At GU cannot see the SA mode Account and User View toggle should not Exists as user is not having any SA Order SA/VA Column should exists in VU data grid 2.Verify the Partner user is directly accessing MCE portal -VU page and able to Submit Order when user not having access to any SA's but having single Install-At GU cannot see the SA mode Account and User View should not Exists as user is not having any SA Order SA/VA Column should exists in VU data grid
22 | Partner User with no SA/multiple GU "Proceed to Order Version Upgrade without a smart account" | 1.Verify the Partner user is redirected from Software Central portal to MCE portal -VU page and able to Submit Order by selecting one of EC GU when user not having access to any SA's but having multiple Install-At GU's can see secondary EC GU selector pop up Account and User View toggle should not Exists as user is not having any SA Order SA/VA Column should exists in VU data grid 2.Verify the Partner user is directly accessing MCE portal -VU page and able to Submit Order by selecting one of EC GU when user having access to multiple SA's and multiple Install-At GU's can see secondary EC selector popup Account and User View toggle should not Exists as user is not having any SA Order SA/VA Column should exists in VU data grid
23 | User is not allowed to place VU orders without SAVA for SA mandatory PID's in User mode / non-SA mode and verify header level error message | Verify and Validate error message and user is not allowed to place VU orders for upgrade eligible products for which smart account is mandatory for those upgrade PID's when User is in User Mode (Seconday End Customer Selector) mode when selected EC GU is not matching with SA Gu's(anchor GU)
24 | Marketing page Validation in all MCE tabs and sub-tabs except Orders and history for Customer/Partner User who don't have access to any SA | Verify marketing page is displayed along with VU hyperlink when Customer/Partner user clicks on other tabs and sub-tabs except History from Version Upgrade page in Non-SA mode for User don't have access to SA
25 | Marketing page Validation in all MCE tabs and sub-tabs except Orders and history for Internal User in User mode | Verify marketing page is displayed along with VU hyperlink when Internal user clicks on other tabs and sub-tabs except History from Version Upgrade page in User mode for Internal User using Switch to User Mode option under SA Selector in VU page
26 | Default Filter -> Product with availability Validation for all the Users | Verify default filter ( Product with Availability) is applied when user lands in MCE portal -VU page directly or via SWC portal In SA or Non-SA mode
27 | Internal User Search by single Traditional contract in User Mode in VU page after selecting GU from Gu selector | Validate the Internal user is able to see VU data for searched Contract and eligible GU in User Mode – Enable Search by one traditional Contract Search by contract and book an order - uma updated
28 | Internal User Search by both Smart and UCSS/ESW contracts in User Mode in VU page after selecting GU from Gu selector | Validate the Internal user is able to see Error message in User Mode when user searches by both Smart and UCSS/ESW contract
29 | Internal User Search by more than 10 contract in User Mode in VU page after selecting GU from Gu selector | Validate the Internal user is able to see Error message in User Mode when user searches more than 10 contracts
30 | Internal User Search by multiple Smart and Traditional contracts and UCSS/ESW and Inactive Install-at and Inactive Bill-to in User Mode | Verify the Internal user is able to see VU data for search traditional and Inactive Instal=at and Bill-to along with error message for UCSS/ESW and Inactive bill-to and Install-at when Internal User placing order on behalf of the Partner/End Customer that having Smart Account on behalf of the Partner/End Customer by searching with multiple (UCSS/ESW and Traditional and Smart and Inactive Install-at or Bill-to )
31 | Internal logging In with Smart Account and submit the order | check the Upgrade product and submit the order

## Global Search
S No | Scenarios | Description
1 | Internal/External User | Select a category from dowpdown and search with a String .Go to Global Search Page and make sure that the Smart Accounts are getting updated based on Category (All Services, All Subscription, All Products, License Features/Summary,Classic Licenses and Devices )selected and the Inventory Views are updated based on Smart Account Selected All -> 1. Search with Device Identifier (or Serial Number if possible) Step 1: Go to Devices - All Devices -> Pick Any one device identifier and perform local search and capture result. Verify correct Device Identifier is displayed. Step 2: Go to GS and search and search Step 1 Device identifier and ensure Filter Category selected as Device (Option). Verify correct Device Identifier is displayed. Step 3: Compare search result (count) between Step 1 and Step 2 and it displayed correct Device Identifier. Step 4: Click on Switch to My Organization View and verify its navigating to correct page and display correct result. 2. Search with Contract Number (Assigned & Unassigned) Step 1: Go to Service Contracts and Subscriptions - All Service Contracts -> Pick Any one Contract Number and perform local search and capture result. Verify correct Contract Number is displayed. Step 2: Go to GS and search and search Step 1 Contract Number and ensure Filter Category selected as Contract Number (Option). Verify correct Contract Number is displayed. Step 3: Compare search result (count) between Step 1 and Step 2 and it displayed correct Contract Number. Step 4: Click on Switch to My Organization View and verify its navigating to correct page and display correct result. 3. Search with SubscriptionId Step 1: Go to Service Contracts and Subscriptions - All Subscriptions-> Pick Any one SubscriptionId and perform local search and capture result. Verify correct SubscriptionId is displayed. Step 2: Go to GS and search and search Step 1 SubscriptionId and ensure Filter Category selected as Subscriptions (Option). Verify correct SubscriptionId is displayed. Step 3: Compare search result (count) between Step 1 and Step 2 and it displayed correct Subscription Id. Step 4: Click on Switch to My Organization View and verify its navigating to correct page and display correct result. 4. Search with PAK Step 1: Go to Licenses - All Classic Licenses-> Pick Any one PAK and perform local search and capture result. Verify correct PAK is displayed. Step 2: Go to GS and search and search Step 1 PAK and ensure Filter Category selected as License Features (Option). Verify correct PAK is displayed. Step 3: Compare search result (count) between Step 1 and Step 2 and it displayed correct PAK. Step 4: Click on Switch to My Organization View and verify its navigating to correct page and display correct result. Note: If you are picking Assigned value then Switch to My Organization View should be enabled otherwise it should be disabled (in case of Unassigned).?
2 | Internal and External user | Count Validation for GS with Switch to My Organization View.
3 | Internal and External User | Perform search on All and pass PAK search by string , user should be able to see the GS result for all the categories.
4 | Internal and External User | PAK search string should not be less than or more than 11 characters.
5 | Internal User | Select a category from dowpdown and search with a String .Go to Global Search Page and select Unknown/Unassigned the coressponding Switch to My Organization View should be disabled
6 | Internal and External user | Validation of Fullscreen view
7 | Internal/External User | Select a category from dowpdown and search with a String .Go to Global Search Page and validate the detailed view for S&S and Devices and make sure that all 4 tabs are present as sub tabs at any point of time
8 | Internal and External user | Validation of Sorting functionality on each column (Sanity : Device Identifier, Contract Number, Subscription Id, PAK and Order Number) a.Perform a sort on a column say Product Number and change the inventory View ----Default one should be displayed . b. Sorting on each column and check the default sort column.
9 | Internal and External user | Column Grid mapping with Main View Columns after clicking on Switch to My Organization View and also in GS results grid
10 | External user | Go to S&S and Devices Tab and make sure if the user is not eligible to see a data appropriate messages are being displayed .
11 | Internal and External User | Verify the place holder text Serial Number , Host ID and MAC ID are replaced by an attribute called Device Identifier for all the search by categories i.e, All, Services and Subscriptions and Devices.
12 | Portal Links
13 | Internal user | Confidence Ranking for License,S&S and Devices Unassigned

## IDV Device_HT
Test Case # | Module | Critical | Testcases | Automate_HT
| ALL DEVICES | Y | Validate external users are able to see all assets (assigned + unassigned) regardless of role | Y
TC_001 | ALL DEVICES | Y | Validate Visual Filters | Y
TC_002 | ALL DEVICES | Y | Validate Left Navigation Filters
TC_003 | ALL DEVICES | Y | Validate Search | Y
TC_004 | ALL DEVICES | Y | Validate Grid-Default Columns and data
TC_005 | ALL DEVICES | Y | Validate Expansion of Parent records | Y
TC_006 | ALL DEVICES | Y | Validate Flyout | Y
TC_007 | ALL DEVICES |  | Validate Alert icon
TC_008 | ALL DEVICES | Y | Validate Manage columns-Additional columns
TC_009 | ALL DEVICES | Y | Validate Full screen,Pagination,Sort
TC_010 | ALL DEVICES | Y | Validate the Assignment Action enablement on Devices via inline, flyout, bulk | Y
TC_011 | ALL DEVICES | Y | Validate the Assignment E2E Flow - inline , flyout action
TC_012 | ALL DEVICES | Y | Validate the Assignment E2E Flow via Select all on Current page - bulk action
TC_013 | ALL DEVICES | Y | Validate the Assignment E2E Flow via Select all on all pages - bulk action
TC_014 | ALL DEVICES |  | Validate the History Events for Assignment
TC_015 | ALL DEVICES | Y | Validate the Reassignment Action enablement on Devices via inline, flyout, bulk
TC_016 | ALL DEVICES | Y | Validate the E2E Flow for Add VA
TC_017 | ALL DEVICES | Y | Validate the E2E Flow for Remove VA
TC_018 | ALL DEVICES | Y | Validate the E2E Flow for Remove n Add VA
TC_019 | ALL DEVICES | Y | Validate the E2E Flow for Remove SA
TC_020 | ALL DEVICES | Y | Validate the E2E Flow for Change SA and Add VA
TC_021 | ALL DEVICES | Y | Validate the Reassignment E2E Flow via Select all on Current page
TC_022 | ALL DEVICES | Y | Validate the Reassignment E2E Flow via Select all on all pages
TC_023 | ALL DEVICES |  | Validate the History Events for Reassignment - Add VA, Remove VA, Change SA, Remove SA
TC_024 | ALL DEVICES | Y | Validation of data displayed in the grid and in the filter behavior in the left navigation filters when removing a specific applied filter
TC_025 | ALL DEVICES |  | Validation of order of filter values displayed in the End OF Support filter
TC_026 | ALL-Device-Export | Y | Individual Data Export | Y
TC_027 | ALL-Device-Export |  | Select all on Current page
TC_028 | ALL-Device-Export |  | Select all on All pages
TC_029 | Licensing | Y | Validate Visual Filters | Y
TC_030 | Licensing | Y | Validate Left Navigation Filters
TC_031 | Licensing | Y | Validate Search | Y
TC_032 | Licensing | Y | Validate Grid-Default Columns and data
TC_033 | Licensing | Y | Validate Expansion of Parent records
TC_034 | Licensing | Y | Validate Flyout
TC_035 | Licensing |  | Validate Alert icon
TC_036 | Licensing | Y | Validate Manage columns-Additional columns
TC_037 | Licensing | Y | Validate Full screen,Pagination,Sort
TC_038 | EOS | Y | Validate Visual Filters | Y
TC_039 | EOS | Y | Validate Left Navigation Filters | Y
TC_040 | EOS | Y | Validate Search | Y
TC_041 | EOS | Y | Validate Grid-Default Columns and data
TC_042 | EOS | Y | Validate Expansion of Parent records
TC_043 | EOS | Y | Validate Flyout
TC_044 | EOS |  | Validate Alert icon
TC_045 | EOS | Y | Validate Manage columns-Additional columns
TC_046 | EOS | Y | Export | Y
TC_047 | EOS | Y | Validate Full screen,Pagination,Sort
TC_048 | Add/Edit Devices | Y | Validate Add/Edit/Delete operation | Y
TC_049 | Add/Edit Devices | Y | Edit All columns and see if its reflecting
TC_050 | OS Version | Y | Validation of data displayed in the data grid when switching between the OS Version Visual Filter / Security Advisories and Field Notices Visual Filter
TC_051 | OS Version | Y | Verify the data displayed in the OS Version data grid when OS Version vf is applied
TC_052 | OS Version | Y | Verify if the data displayed in the columns is correct for a specific os version -- OS Version visual filter is applied
TC_053 | OS Version | Y | Validation of search functionality - -- OS Version visual filter is applied | Y
TC_054 | OS Version | Y | Validation of filter functionality - -- OS Version visual filter is applied | Y
TC_055 | OS Version | Y | Validation of pagination functionality in the data grid and OS Health Flyout - -- OS Version visual filter is applied
TC_056 | OS Version | Y | Validation of search functionality in the os version flyout -- OS Version visual filter is applied
TC_057 | OS Version | Y | Validation of data displayed in the data grid when the VA selection is changed - -- OS Version visual filter is applied
TC_058 | OS Version | Y | Validation of data displayed in the OS Version flyout - -- OS Version visual filter is applied
TC_059 | OS Version | Y | Validation of sort functionality in the OS version flyout -- OS Version visual filter is applied
TC_060 | OS Version | Y | Validation of search functionality in the os version flyout -- OS Version visual filter is applied
TC_061 | Field Notice | Y | Validation of filter functionality
TC_062 | Field Notice | Y | Validation of search functionality
TC_063 | Field Notice |  | Validation of UI functionality
TC_064 | Field Notice | Y | Validation of search functionality in the field notice flyout
TC_065 | Field Notice | Y | Validation of columns displayed in the data grid | Y
TC_066 | Field Notice | Y | Validation of data displayed in the data grid when Impacted devices filter is applied from field notices visual filter
TC_067 | Field Notice | Y | Validation of data displayed in the field notice flyout
TC_068 | Field Notice | Y | Validation of data displayed in the flyout when no device is available in the potentially vulnerable section
TC_069 | Field Notice | Y | Validation of sort functionality in the data grid and field notice flyout | Y
TC_070 | Security Advisories | Y | Validate if data displayed in the Security Advisories data grid is sorted on severity
TC_071 | Dashboard | Y | Validation of data displayed in the Dashboard tab | Y
TC_072 | Dashboard | Y | Validation of KPI Headers | Y
TC_073 | Dashboard | Y | Validation of KPI Header count | Y
TC_074 | Dashboard | Y | Validation of micro interactions from Device LDoS widget | Y
TC_075 | Dashboard | Y | Validation of micro interaction from Expiration S&S widget | Y
TC_076 | Dashboard |  | Validation of text message displayed when applied Arch/Count filter doesn’t have data in other widget
TC_077 | Dashboard | Y | Validation of data displayed in teh Assign Status widget when applied Arch or country filter doesnt have data in anyof the categories | Y
TC_078 | USER MODE | Y | Data grid
TC_079 | Service Coverage | Y | Export data
TC_080 | Field Notice | Y | Export - data for impacted devices
TC_081 | Licensing | Y | Export
TC_082 | OS Version | Y | Export - data
TC_083 | Service Coverage | Y | Local Search | Y
TC_084 | Service Coverage | Y | Left Navigation Filter validation (ALL SERVICE COVERAGE)
TC_085 | Service Coverage | Y | Left Navigation Filter validation (SERVICE COVERAGE: Not Covered)
TC_086 | Service Coverage | Y | Left Navigation Filter validation (SERVICE COVERAGE: Covered)
TC_087 | Service Coverage | Y | Main Grid Columns (Service Coverage: Not Covered)
TC_088 | Service Coverage (Device) | Y | Validate Visual Filters | Y
TC_089 | Service Coverage | Y | Validate Left Navigation Filters
TC_090 | Service Coverage (Device) | Y | Validate Search | Y
TC_091 | Service Coverage | Y | Validate Grid-Default Columns and data
TC_092 | Service Coverage | Y | Validate Expansion of Parent records
TC_093 | Service Coverage | Y | Validate Flyout
TC_094 | Service Coverage | Y | Validate Flyout
TC_095 | Service Coverage | Y | Validate applying multiple filters across the application
TC_096 | Service Coverage | Y | Validate + icon expansion of parent record
TC_097 | Service Coverage | Y | Validate Parent/Child displayed in Main grid
TC_098 | Service Coverage | Y | Validate show more option of left navigation filter (applicable for all tabs)
TC_099 | Service Coverage |  | Validate Pagination (Performance)
TC_100 | Service Coverage |  | Validate Screen resolution issues
TC_101 | USER MODE | Y | Validate expanding parent record
TC_102 | USER MODE | Y | Visual Filter validation
TC_103 | USER MODE | Y | Left Navigation Filter validation
TC_104 | USER MODE | Y | Local Search
TC_105 | USER MODE | Y | Main grid attribute validation
TC_106 | USER MODE | Y | Validate Local Search
TC_107 | USER MODE | Y | Validate Delete functionality
TC_108 | USER MODE |  | Validate Left navigation filter
TC_109 | USER MODE | Y | Validate VF Filter
TC_110 | Security Advisories | Y | Validate the columns , sort icon displayed on the columns in the security advisory data grid
TC_111 | USER MODE | Y | Data grid
TC_112 | Service Coverage (Device) | Y | Export data | Y
TC_113 | LICENSING-SMART/CLASSIC | Y | Validate Left Navigation Filters | Y
TC_114 | Event log |  | Validate Sort functionality in Event log tab
TC_115 | Event log |  | Validate Pagination,Filter
TC_116 | Service Coverage | Y | Validate Action for (ALL: Service Coverage) view
TC_117 | Service Coverage | Y | validate Action for (Not Covered: Service covergae)view
TC_118 | (S&S) -Subscription | Y | Subscriptions-Validate Left Navigation Filters
TC_119 | (S&S) -Subscription | Y | Subscriptions-Validate Search | Y
TC_120 | (S&S) -Subscription | Y | Subscriptions-Validate Grid-Default Columns and data
TC_121 | (S&S) -Subscription | Y | Subscriptions-Validate Product setails view(micro-interaction from summary to product view)
TC_122 | (S&S) -Subscription | Y | Subscriptions-Validate Manage columns-Additional columns
TC_123 | (S&S) -Subscription | Y | Subscriptions-Validate Full screen,Pagination,Sort
TC_124 | (S&S) -Subscription | Y | Subscriptions-Validate left nav and VF combination
TC_125 | (S&S) -Contracts | Y | Contracts-Validate Left Navigation Filters
TC_126 | (S&S) -Contracts | Y | Contracts-Validate Search | Y
TC_127 | (S&S) -Contracts | Y | Contracts-Validate Grid-Default Columns and data
TC_128 | (S&S) -Contracts | Y | Contracts-Validate Product setails view(micro-interaction from summary to product view)
TC_129 | (S&S) -Contracts | Y | Contracts-Validate Manage columns-Additional columns
TC_130 | (S&S) -Contracts | Y | Contracts-Validate Full screen,Pagination,Sort
TC_131 | (S&S) -Contracts | Y | Contracts-Validate left nav and VF combination
TC_132 | (S&S) -Contracts | Y | Contracts - Micro interaction from All contracts to All products
TC_133 | (S&S) -ALL products | Y | Products-Validate Left Navigation Filters | Y
TC_134 | (S&S) -ALL products | Y | Products-Validate Search (Subcription & Contracts) | Y
TC_135 | (S&S) -ALL products | Y | Products-Validate Grid-Default Columns and data (subcription & contracts)
TC_136 | (S&S) | Y | Products-Validate Product setails flyout
TC_137 | (S&S) -ALL products | Y | Products-Validate Manage columns-Additional columns
TC_138 | (S&S) -ALL products | Y | Products-Validate Full screen,Pagination,Sort
TC_139 | (S&S) -ALL products | Y | Products-Validate left nav and VF combination | Y
TC_140 | (S&S) - Export | Y | S&S - Export (Validate export functionality for Subscription/All Prod/Service Contracts, Software and EA) | Y
TC_141 | Security Advisories | Y | Validation of UI capabilities
TC_142 | Security Advisories | Y | Validation of filter functionality
TC_143 | Security Advisories | Y | Validation of Search functionality | Y
TC_144 | Security Advisories | Y | Validation of Search functionality after applying Critical or High filters
TC_145 | Security Advisories | Y | Validation of Filter functionality after applying critical or high filters
TC_146 | Security Advisories | Y | Validation of counts displayed in the data grid when applying Critical or High filters i.e the counts displayed in the visual filter is matching with the counts displayed in the data grid
TC_147 | Security Advisories | Y | Validation of Pagination functionality
TC_148 | Security Advisories | Y | Validation of Vulnerable and Potentially Vulnerable devices count displayed in the data grid with respect to the flyout after applying different filters | Y
TC_149 | Security Advisories | Y | Validation of columns displayed in the Security Advisory Flyout
TC_150 | Security Advisories | Y | Validation of search functionality in the Security Advisory flyout
TC_151 | Security Advisories | Y | Validation of sort functionality in the Security Advisory flyout
TC_152 | Security Advisories | Y | Validation of Manage Columns flyout
TC_153 | VA Selector | Y | Validation of VA Selector when Not in SA is selected from Smart Account Assignment filter

## Regular MCE Device TCs
S No | Scenarios | Description
Devices
1 | Inventory view | user with method 'Internal View All' sees All, Assigned & Unassigned View
2 | Main Grid | User is able to navigates from Dashboard to Devices by clicking 'View Asset'/hyperlink on widget
3 | Main Grid | When user navigates from Dashboard to Devices , filters are applied on Main Grid and count matches
4 | Detail View | Device Name hyperlink takes to Device Detail Overview tab
5 | Software Only Filter | this filters is not shown on Unassigned view . In assigned view , it shows only non threaded ESM assets mainly the Smart devices .
6 | Confidence Ranking | Confidence ranking column should never be empty for interal and it should be properly color coded meaning if Green raning is selected , Confidence ranking column is shown in Green color and text is 'Green' . Like wise if Yelllow ranking is selected , show ranking in Yellow color and text is 'Yellow'
7 | Filters | Validate the Filters displayed in Devices View- Static Filters Inventory View(Only User having 'IVA' or 'ASA' method) End Of Support (Options -> Not passed, Within 3 months, within 12 months, Has passed, Custom Date) Coverage (Options-> Covered, not Covered, Software Only) Coverage End Date(Within 30 days, Within 31 to 60 days, Within 61 to 90 days, Custom Date) Warranty(Options-> Under Warranty, Not Under Warranty) Confidence Ranking (Options -> Green, Yellow) Customer Country Architecture Sub-Architecture (Dynamic filter, filter appears if records less than 100K ) Customer Name (Dynamic filter, filter appears if records less than 100K ) Customer Site ID (Dynamic filter, filter appears if records less than 100K ) Software version (Dynamic filter, filter appears if records less than 100K )
8 | Search Options and search functionality | Validate the Search functionality for the below attributes displayed in Devices View- Search All Product Number Product Description Device Identifier Contract Number Customer Name Customer Site ID Device Name Smart Product Instance Name
9 | Main Grid - Mouse Hover | Validate the Mouse hover to see hover text on few columns and Filters Address pop -up on Map icon->Customer Site ID, (+) View more functionality -> Virtual Account, Device Identifier and sort on Header Columns(Product Number by default in asc).
10 | Personalized View | Validate the user is able to create or edit local Personalised View by applying Filters, manage columns(select/deselect), change column order, sort,pagination.
11 | Personalized View | Validate the User is able to set the User preferred view as "Default View" by clicking on "Set as Default" button.
12 | Personalized View | Validate the edit and delete icons are not displayed for "MCE Default" View.
13 | Personalized View | MCE default personlized view should be at the top in personlized view list and other user created personalized view can be displayed in ascending order

## KPIs
# | Flow | Track | Scenario | Automated
1 | Service Coverage by Architecture | Account Overview | Select an Architecture (List View) and Click on any hyperlinked values . The user should navigate to the required tab with the appropriate filters | Y
2 | Expiration of Service Contracts by Architecture | Account Overview | Select an Architecture (List View) and Click on any hyperlinked values . The user should navigate to the required tab with the appropriate filters | Y
3 | Device Ldos by Architecture | Account Overview | Select an Architecture (List View) and Click on any hyperlinked values . The user should navigate to the required tab with the appropriate filters | Y
4 | Service Coverage by Country | Account Overview | Select Country (List View) and Click on any hyperlinked values . The user should navigate to the required tab with the appropriate filters | Y
5 | Expiration of Service Contracts by Country | Account Overview | Select Country (List View) and Click on any hyperlinked values . The user should navigate to the required tab with the appropriate filters | Y
6 | Device Ldos by Country | Account Overview | Select Country (List View) and Click on any hyperlinked values . The user should navigate to the required tab with the appropriate filters | Y
7 | Assign Status | Account Overview | Select an Architecture and Click on any hyperlinked values . The user should navigate to the required tab with the appropriate filters. (Assigned count from License Summary, Unassigned Count from Classic License Page) | Y
8 | KPI | All Service Contract | UI - Verify data between KPI and Result page by clicking on each section link (Status, Earliest Expiration) | Y
9 | KPI | All Subscriptions | UI - Verify data between KPI and Result page by clicking on each section link (Status, Earliest Expiration) | Y
10 | KPI | All Products | UI - Verify data between KPI and Result page by clicking on each section link (LDos, Expiration) | Y
11 | KPI | License Summary | UI - Verify data between KPI and Result page by clicking on each section link (License Type, Expiration, Balance) | Y
12 | KPI | All Classic Licenses | UI - Verify data between KPI and Result page by clicking on each section link (Eligible for Smart Conversion, Classic License Fulfillment) | Y
13 | KPI | All Devices | UI - Verify data between KPI and Result page by clicking on each section link (Licensing, Service Coverage, End of Support) | Y
14 | KPI | Product Support Info | UI - Verify data between Flyout/KPI and Result page by clicking on each section link (OS Version, Field Notices, Security Advisories) | Y
15 | Flyout | All Devices | UI - Verify Below details from Device Page 1. Product details - Count, Hardware Type 2. Service Details - Line Status 3. Purchase & Warranty - Warranty Status 4. License Feature 1. Count 2. Check whether you able to bring the table print in the report 5. Alert Total count alerts Vulnerable status (overall under field Notices) 6. Device Actions check from three dots it should match between main grid and flyout actions (Not possible to automate because actions are not able to capture enabled / disabled, its bit different in MCE compare to other UI's) | Y